## Master QA Tracker
ID | Module | Page | UI Element | Type | Expected Behaviour | Actual Behaviour | Priority | Status | Tester | Remarks
LP-01 | Landing | Hero | Start Learning | Button | Login if guest; Learning if logged in | Opens wrong/no flow | Critical | Open
LP-02 | Landing | Hero | Create Account | Button | Open Register | No action | High | Open
LP-03 | Landing | Layout | Hero spacing | Layout | Balanced spacing | Large top gap | Medium | Open
LP-04 | Landing | Cards | All feature cards | Navigation | Open modules | Some inactive | High | Open
LP-05 | Landing | Footer | All links/icons | Links | Navigate/open external | Inactive | High | Open
LG-01 | Login | Form | Sign In | Form | Authenticate | Inactive | Critical | Open
LG-02 | Login | OAuth | Google/GitHub | OAuth | Redirect backend | Inactive | High | Open
RG-01 | Register | OTP | Registration flow | Flow | OTP->Dashboard | Wrong redirect | Critical | Open
DB-01 | Dashboard | Header | Theme toggle | Toggle | Persist theme | Inactive | Medium | Open
DB-02 | Dashboard | Header | Notifications | Dropdown | Open notifications | Inactive | Medium | Open
DB-03 | Dashboard | Cards | Statistics | Data | Backend-ready | Hardcoded | Medium | Open
TR-01 | Translator | Language | Selector | Dropdown | Multiple languages | Limited | Medium | Open
TR-02 | Translator | Signa | Conversation | Feature | Dummy AI | Static | Medium | Open
LE-01 | Learning | Lessons | Continue | Button | Resume lesson | Inactive | Medium | Open
PR-01 | Profile | Avatar | Upload | Upload | Choose image | Inactive | Medium | Open
ST-01 | Settings | Privacy | Manage Data | Button | Open modal | Inactive | Medium | Open

## Navigation Checklist
Page | Element | Destination | Pass/Fail | Notes

## UI Layout Review
Page | Alignment | Spacing | Typography | Responsive | Animations | Status | Notes

## Button Audit
Page | Button | Works? | Loading | Disabled | Hover | Focus | Backend Ready | Notes

## Form Validation
Form | Validation | Errors | Success | API Ready | Status

## Responsive Test
Page | Desktop | Laptop | Tablet | Mobile | Issues

## Backend Readiness
Module | API Endpoint | Request | Response | Frontend Ready | Remarks

## Deployment Checklist
Item | Status | Remarks